## Risk Assessment
Project Name: |  | SCRIBE
Group Name: |  | Hypertechs-2.0
RISK MANAGEMENT PLAN
ITEM # | TOPIC | RISK | CONTROL ENVIRONMENT | RISK ASSESSMENT | CONTROL ACTIVITIES | MONITORING | INFORMATION AND COMMUNICATIONS | RISK JUDGEMENT | LIKLELIHOOD | IMPACT | RISK LEVEL | COMMENTS
1 | Data Security | Unauthorized access to user notes | Secure authentication, encryption standards | High | Implement strong password policies | Regular security audits, logging of access | User data encryption protocols communicated to users | High Priority | Likely | Severe | High | Regularly update security measures
2 | System Failure | Server downtime leading to inaccessibility of the app | Redundant servers, regular maintenance schedules, disaster recovery plans | Medium | Implement failover systems, conduct regular maintenance, establish clear disaster recovery plans | Monitor server performance and uptime statistics | Regular updates to users regarding maintenance schedules and expected downtimes | Medium Priority | Possible | High | Medium | Ensure timely updates and backups
3 | Data Loss | Accidental deletion or corruption of user data | Data backup procedures, version control, data integrity checks | High | Regular automated backups, version control systems, periodic data integrity checks | Regular review of backup procedures | Clear communication to users about backup procedures and data recovery options | High Priority | Possible | Severe | High | Test backup and recovery processes regularly
4 | Scalability | Inability to handle increased user load leading to degraded performance | Scalable architecture, load balancing, performance tuning | Medium | Implement scalable architecture, use load balancing techniques, conduct performance tuning | Monitor usage and performance metrics | Communicate scalability efforts and system capabilities | Medium Priority | Possible | Moderate | Medium | Plan for future growth and scalability
5 | Performance | Poor app performance leading to a suboptimal user experience | Performance monitoring tools, code optimization practices | Medium | Optimize code, implement performance monitoring tools, conduct load testing | Monitor app performance metrics | Inform users of performance optimization efforts | Medium Priority | Possible | Moderate | Medium | Address performance issues proactively
6 | Usability | User interface issues causing confusion and poor user experience | User feedback mechanisms, usability testing processes | Medium | Conduct regular usability testing, gather and act on user feedback | Track user feedback and usability test results | Inform users of usability improvements and changes | Medium Priority | Possible | Moderate | Medium | Continuously improve based on feedback
7 | Core | Core functionalities (Home, Notes, To-Do, Folders, Trash) facing functional disruptions | Unit tests, integration tests, continuous deployment | High | Implement thorough testing procedures, continuous integration and deployment processes | Monitor core functionality performance | Inform users about core updates and improvements | High Priority | Possible | High | High | Regularly test and update core features
8 | Assets | Loss or corruption of assets (Images, Fonts) | Asset management protocols, version control | Medium | Implement asset management policies, version control for assets | Regularly review asset management processes | Inform users about asset management and recovery options | Medium Priority | Unlikely | Moderate | Low | Maintain asset version control